## Budget
PATTI GOULD - GUEST BATHROOM REMODEL
636 Ambrose Lane, Orange County, CA
LABOR & SERVICES
Demo (vanity, tub, fixtures, flooring, tile) | 800 | Full removal & disposal
Hot Mop (shower pan waterproofing) | 400 | Critical for mold prevention
Tile Installation - Bathroom Floor (21 sq ft @ $35/sq ft) | 735 | Professional installation
Tile Installation - Shower Walls (90 sq ft) | 2000 | High-quality labor
Bathtub Installation & Set | 560 | Leveled, secured, sealed
Double Sink Vanity Installation | 1680 | Wall-mounted built-in
Vanity Countertop Installation | 1120 | Sealing & finish
Glass Shower Enclosure (frameless) | 1820 | Custom fit installation
Plumbing (rough-in + finish) | 1260 | Dual sinks + tub/shower diverter
Electrical (lighting, GFCI, vent fan) | 280 | Code-compliant
Drywall / Backer Board / Substrate Prep | 560 | Surface preparation
SUBTOTAL - LABOR & SERVICES | 11215
MATERIAL ALLOWANCES
Tile - Bathroom Floor Material | 600 | 18-24 sq ft / ceramic or porcelain
Tile - Shower Wall Material | 700 | 80-100 sq ft spray zone
Sink Faucet (Dual) | 250 | Mid-range quality
Shower Valve & Trim Kit | 150 | Standard valve body
Project Management & Contingency | 1485 | Coordination & unforeseen items
SUBTOTAL - MATERIAL ALLOWANCES | 3185
TOTAL PROJECT INVESTMENT | 14400
NOT INCLUDED IN THIS QUOTE
City Permits & Inspection Fees | $100-$300 | Paid directly to city
Material Upgrades Beyond Allowances | Varies | Any premium selections
Structural Modifications | Varies | Wall relocation if needed
Change Orders | Varies | Work discovered during demo

## Timeline
PROJECT TIMELINE
Phase | Duration | Notes
Pre-Construction (permits + material selection) | 1 week | Final selections, permit submission
Demolition & Prep | 3-4 days | Remove fixtures, repair substrate
Plumbing & Electrical (rough-in) | 4-5 days | Supply lines, drains, electrical rough
Flooring & Tile Work | 5-7 days | Install flooring, tile, grout, seal
Fixtures & Hardware Installation | 3-4 days | Tub, vanity, faucets, enclosure
Final Walk-Through & Cleanup | 1 day | Touch-ups, cleanup, walkthrough
TOTAL ESTIMATED DURATION | 3-4 weeks